## Format
Proposal Needs List Japan
0
Customer: |  | Volvo Powertrain | [5 empty] | Proposal No. | 1104
Location: |  | Ageo, Japan | [5 empty] | Proposal Leader: | Chris Clark
Description: |  | New Engine Paint System | [5 empty] | Date: | 2012-05-11
ITEM | INFORMATION REQUIRED |  | REQUEST | PERSON(S) | DATE |  |  | STATUS / COMMENTS
NO. |  |  | BY | RESP. | REQUEST | DUE | COMPLETE
General Items
1 | Need signed contract |  |  | Koachi | Week 17 | Week 20 |  |  |  | Name | Abreviation
2 | Next F2F meeting in Japan |  |  | CC | Week 17 | Week 23 |  | Need input from Ageo |  | Johan Bergman | JJB
3 | FAT in india |  |  | CC | Week 17 | Week 21 |  | Engine and skid delivery, Visas |  | Scott Henson | SH
4 | Mater Schedule |  |  | CC | Week 15 | Week 20 |  | Awaiting final drawing approvals |  | Pete Cipollina | PC
5 | Engines, Skids, Visas |  |  | YK | Week 19 | ? |  | Need to know when conveyor supplier expects tohave on site |  | Leif Josefsson | LJ
6 | Laydown area for multiple containers |  |  | YK | Week 15 | Week 20 |  | Need to identify multiple container storage |  | Bob Cheesman | BC
Electrical/Controls | [9 empty] | Bob Cheesman III | RC
1 | Remove the HMI from conveyor control provide one additional stand-alone HMI with 100V power plug and one Profi-Net plug. |  | YK | PC | Week 13 | Week 15 | Week 19 | waiting for Volvo Japan reply, cost and drawing approval Week 17 - PMPF instructed Controls Contractor to proceed with this request Week 19 - approved by Volvo Japan |  | Aaron Howell | AH
2 | Additional 100V power for each stand-alone HMI (3) must be powered and wired from the conveyor control panel |  | YK | PC | Week 13 | Week 15 | Week 19 | waiting for Volvo Japan reply, cost and drawing approval Week 17 - PMPF instructed Controls Contractor to proceed with this request Week 19 - approved by Volvo Japan |  | Chris Clark | CC
3 | Additional Profi-Net plug in each stand-alone HMI (3) must be connected (wired) to conveyor Profi-Net comm system |  | YK | PC | Week 13 | Week 15 | Week 19 | waiting for Volvo Japan reply, cost and drawing approval Week 17 - PMPF instructed Controls Contractor to proceed with this request Week 19 - approved by Volvo Japan |  | Jeff Busic | JB
4 | Provide solenoid valve for paint kitchen compressed air supply piping, 24VDC if possible, normally closed powered open |  | YK | PC | Week 13 | Week 15 | Week 19 | waiting for Volvo Japan reply, cost and drawing approval Week 17 - PMPF instructed Controls Contractor to proceed with this request Week 19 - approved by Volvo Japan |  | Yousuke Kojima | YK
5 | Wire compressed air solenoid into process equipment control valve emergency stop (E-Stop) circuit. |  | YK | PC | Week 13 | Week 15 | Week 19 | waiting for Volvo Japan reply, cost and drawing approval Week 17 - PMPF instructed Controls Contractor to proceed with this request Week 19 - approved by Volvo Japan
6 | Paint Kitchen exhaust fan needs to be wired so it will operate 24 hours a day. It will be powered and controlled from the process control panel and manually started and stopped from a pushbutton control station at the paint kitchen location |  | YK | PC | Week 13 | Week 15 | Week 19 | waiting for Volvo Japan reply, cost and drawing approval Week 17 - PMPF instructed Controls Contractor to proceed with this request Week 19 - approved by Volvo Japan
7 | Add 1 local conveyor “Take IN/OUT” manual control station. Operators to include: o lift table up PB o lift table down PB o lift tale forward PB o lift table reverse PB o OUT lift table auto/manual SS o IN lift table auto manual SS |  | YK | PC | Week 13 | Week 15 | Week 19 | waiting for Volvo Japan reply, cost and drawing approval Week 17 - PMPF instructed Controls Contractor to proceed with this request Week 19 - approved by Volvo Japan
8 | Safety Relays - Pilz in lieu of Rockwell |  | YK | PC | Week 15 | Week 17 |  | waiting for Volvo Japan reply, cost and drawing approval Week 17 - PMPF instructed Controls Contractor to proceed with this request
9 | Safety Light Curtain - Sick in lieu of P&F |  | YK | PC | Week 15 | Week 17 | Week 19 | waiting for Volvo Japan reply Week 19 - PMPF will purchase Sick Safety Ligh Curtains as oart of original scope
10 | Photo Sensor - IFM in lieu of P&F |  | YK | PC | Week 15 | Week 17 | Week 21 | waiting for Volvo Japan reply, cost and drawing approval Week 17 - PMPF instructed Controls Contractor to proceed with this request
11 | Prox Sensor - IFM in lieu of P&F |  | YK | PC | Week 15 | Week 17 | Week 21 | waiting for Volvo Japan reply, cost and drawing approval Week 17 - PMPF instructed Controls Contractor to proceed with this request
12 | Robot Interlocks as per attached email |  | YK | PC | Week 15 | Week 17 | Week 21 | waiting for Volvo Japan reply, cost and drawing approval Week 17 - PMPF instructed Controls Contractor to proceed with this request
13 | Conveyor control panel customer approval |  | YK | PC | Week 15 | Week 17 |  | waiting for Volvo Japan reply
14 | Conveyor control BOM customer approval |  | YK | PC | Week 15 | Week 17 |  | waiting for Volvo Japan reply
15 | Conveyor pushbutton station customer approval |  | YK | PC | Week 15 | Week 17 | Week 19 | waiting for Volvo Japan reply Week 19 Volvo Japan approved
16 | Process control panel customer approval |  | YK | PC | Week 15 | Week 17 |  | waiting for Volvo Japan reply
17 | Process control BOM customer approval |  | YK | PC | Week 15 | Week 17 |  | waiting for Volvo Japan reply
18 | Paint Kitchen operator station customer approval |  | YK | PC | Week 15 | Week 17 |  | waiting for Volvo Japan reply, cost and drawing approval Week 17 - PMPF instructed Controls Contractor to proceed with this request
19 | Safety Zone identification |  | YK | PC | Week 15 | Week 17 | Week 19 | Week 19 - approved by Volvo Japan
20 | Bar Code Scanner requirements |  | PC | YK | Week 18 | Week 19 |  | waiting for volvo Japan
Mechanical
1 | Paint kitchen exhaust duct building exit through window |  | CC &YK | Week 19 | Week 21 |  |  | Kojima to help Chris best window to penetrate
2 | Lift table redesign (relocate lift motor) |  | YK | Week 19 | Week ? |  |  | Will cause delay in schedule
3 | Final drawing approval from Japan |  | AH | Week 17 | Week 20 |  |  | Prints back from Kojima. Waiting for response from India
4 | Need quote from Techsus for arial work |  | CC &YK | Week 17 | Week 20 |  |  | Kojima helping Chris with translation/Thank you
5 | Flow meter decision |  | SH | Week 19 | Week 20 |  |  | Quote sent to Scott
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
Pneu-Mech Paint Facilities LLC
3595 East US Highway 70
Claremont , North Carolina 28610

## Compatibility Report
Compatibility Report for Copy of Japan Needs List.xls
Run on 5/11/2012 17:28
The following features in this workbook are not supported by earlier versions of Excel. These features may be lost or degraded when opening this workbook in an earlier version of Excel or if you save this workbook in an earlier file format.
Minor loss of fidelity | # of occurrences | Version
Some cells or styles in this workbook contain formatting that is not supported by the selected file format. These formats will be converted to the closest format available. | 8 | Excel 97-2003